## 24D Books
SNO | Issue | Issue Given By | IssueType | Team | Allocated | Status
1 | While doing any pending transaction After getting pending popup Click on ' X "Button Automatically Application Closing. | Testing Team | Bug | Technical | Sujan
2 | Under Favorites displaying More than 10 items after Saving First time transaction ,under recent activity are not getting after relogging it is displaying | Testing Team | Bug | Technical | Sujan
3 | Import Party opening Balance Screen :Following fields are not working 1.voucher Series 2.Voucher types 3.Invoice template | Testing Team | Req | Technical | Sujan / Sudheer Sir
4 | Need to Change the logo while creating company [ New logo ] | Sudheer sir | Req | Technical | Sujan / Sudheer Sir
5 | Configure Page should be the default | Sudheer sir | Req | Technical | Shaker / Sudheer Sir | Done
6 | Change Icons in Configure Page | Sudheer sir | Req | Technical | Sujan / Sudheer Sir
7 | Rename Configure Page as Settings | Sudheer sir | Req | Technical | Sujan / Sudheer Sir
8 | Startup page required for every master. | Sudheer sir | Req | Technical | Sujan / Sudheer Sir
9 | Settings required to enable apps. | Sudheer sir | Req | Technical | Sujan / Sudheer Sir
10 | Change Icons for Master, Transaction and Report. | Sudheer sir | Req | Technical | Shaker / Sudheer Sir
11 | If no properties exist, then show "No properties for this master". | Sudheer sir | Req | Technical | Shaker / Sudheer Sir
12 | Rename Search FEature Settings as "Search Settings". | Sudheer sir | Req | Technical | Shaker / Sudheer Sir
13 | Show search settings in the settings header on the right side. | Sudheer sir | Req | Technical | Shaker / Sudheer Sir
14 | Give Show Helplinks in the settings page | Sudheer sir | Req | Technical | Shaker / Sudheer Sir
15 | Each Setting to have it's own help link. | Sudheer sir | Req | Technical | Shaker / Sudheer Sir
16 | Default Dashboards | Sudheer sir | Req | Technical | Shaker / Sudheer Sir
17 | Don't show empty rows in Address in Company section in Settings page. Reduce the line spacing | Sudheer sir | Req | Technical | Shaker / Sudheer Sir
18 | Key Metrics Page Required | Sudheer sir | Req | Technical | Shaker / Sudheer Sir
19 | Redo Workbench page UI | Sudheer sir | Req | Technical | Shaker / Sudheer Sir

## 24E Classic M
SNO | Issue | Issue Given By | IssueType | Allocated | Status
1 | Group Ledger-Unable to add Master Properties/Nodes of Account | Branch | Bug | Sujan
2 | The GST Rates Which is not enabled in 12K is getting enabled while converting to 14K | Branch | Bug | Sujan
4 | 12K to 14K migration -how to treate Debtors and Supplier Created in Different Nodes for Reporting Purpose | Branch | ToDiscuss with Sudheer Sir | Sujan
5 | Masters created in one client system are not appearing in another system, even after clearing cache through the tool menu.Need to delete the Local Cache folder form App data folder | Branch | Bug | Aziz
6 | Pivot Functionality in Print (HSN Summary/Ratewise Summary) | Branch | Requirement
7 | Same Voucher No showing as subsiquent Link so unable to Edit ir delete Transactions | Branch | Bug | Shaker
8 | Default Country Required |  | Requirement | Sujan
9 | Details not captured after E-Invoice Re submission (1. Ack Date & QR Code) its working after remove local cache folder & re login, long process | Branch |  | Srinivas
10 | When unselect Administrator rights in Users - There is not coming Tax Menu & also its transaction & screen (E-Invoice Offline/Reports, E-Invoice Re Submission, Pending E-Ivnoice Report, GSTR Transaction & Reports, EWay bill & REports) | Branch | Please discuss with Sandeep | Srinivas
11 | Print format not transferred in 24E from 22E (Cash Payment, Bank Payment, Journal Voucher, Book Expense or Receivables) | Branch |  | Shaker
12 | While import print format from 22E then coming error while printing & editing to related print format. | Branch |  | Shaker
13 | Month wise P&L Authorisations in Browser Multiple Email, SMS and WhatsApp Templates per transaction Scheduled Emails with formatted reports | Sudheer sir
14 | Comparative Columns in P&L and Balance Sheet | Sudheer sir |  | Subham
15 | Month wise Comparative P&Ls | Sudheer sir
3 | Profitability Report - Margin % is showing wrong | Branch | Bug

## Genera - Finance
SNO | Issue | IssueType | Allocated
1 | Trial Balance Last Month | Functional
2 | Required Tally financial statements formats in 24D-Books [P&L,TB,B/S, Funds flow & Cashflow] | Functional
3 | Master Deletion is required, for those masters which is not done any transactions | To Discuss
4 | Tally or Generic API integration options required | To Discuss | Aziz
5 | All API like PAN, GSTNo and Etc… | To Discuss | Srinivas
6 | Quarterly GST filling | Functional | Srinivas
7 | Bulk Invoice and E-Invoice option is required | To Discuss | Done / Shaquid / Sujan
8 | Pin to Pin Distance | To Discuss | Srinivas
9 | Slab GST required | To Discuss
10 | Monthly wise Valuation | Functional
11 | T form TB is required | Functional
12 | Need to require Prieod wiseTrial Balance report | Functional
13 | E-mail facility not done. | Requirement | Done
14 | As there is a option of Bulk Print for Vouchers but unable to print it. | Bug | Shaker
15 | Configured reports not transferred from 12K to 14K | Bug | Done
16 | Even after user logout in launcher, session is exists in server | To Discuss | Aziz
17 | Cache issue | To Discuss | Aziz
18 | Link transactions are appearing only when use right click Windows admin login, else transaction links are not showing | Requirement | Done
19 | Check the transaction copy option | Requirement | Done
20 | 2B Reconsilation | To Discuss | Srinivas
21 | Option to Cancell eWay Bill and eInvoice | To Discuss | Srinivas
22 | 24E License are frequently Expiring and shows error "Client ID already been activated" | Bug | Venkat
23 | Error Messages in Client Launcher- Not getting Proper Error Messages thru Client Launcher,Its getting a General Message "Unable to Process Server Request" | Bug | Venkat
24 | Sending Invoice Link Thru SMS | To Discuss | Aziz
25 | Provide multiple template in SMS confifuration | To Discuss | Aziz
26 | Logout Users should remove from Server | Requirement | Venkat